## Product Backlog (Scrum)
MoSCoW ID | Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | User | Scrum Team Assigned | Complexity | Risk/ Impact | Work Product Cross Reference/Details sheet | Business Process | Type | Primary Actors | Secondary Actors | Comments | Acceptance Criteria | Completeness Criteria | User Acceptance Test Case ID | Comments
1 | 1 | document | M | US:01 | Sign up | User |  | Average |  |  | User has to first signup in order to login. Here we assign details like Name,designation,gender,date of birth,email id,password.
2 | 2 | document | M | US:02 | login | User |  | Average |  |  | After signing up, the admin can login into the page by entering their ID/name and password.
3 | 3 | document | S | US:03 | Forgot password | User |  | Average |  |  | If the user credentials are incorrect,User will not able to login.Then by using Forgot password, user can change password successfully
4 | 4 | document | M | US:04 | Track raw materials | User |  | Complex |  |  | User has to enter order ID of raw materials, and get all the details of particular order ID
5 | 5 | document | S | US:05 | Update raw materials | User |  | Complex |  |  | User has to enter Raw material order ID and set manufacturing date and expiry date, then all details are inserted in database and data inserted message is shown
6 | 6 | document | M | US:06 | Track products | User |  | Complex |  |  | User has to enter order ID of Product order, and get all the details of particular order ID
7 | 7 | document | S | US:07 | Update products | User |  | Complex |  |  | User has to enter product order ID and set manufacturing date and expiry date, then all details are inserted in database and data inserted message is shown
8 | 8 | document | M | US:08 | Update raw materials order | User |  | Average |  |  | User has to enter Raw material order id and new delivery status and then delivery status is updated
9 | 9 | document | M | US:09 | Update products order | User |  | Average |  |  | User has to enter product order id and new delivery status and then delivery status is updated
10 | 10 | document | S | US:10 | Place raw material order | User |  | Average |  |  | User has to enter all the details of raw material order and so that order is placed successfully is shown
11 | 11 | document | S | US:11 | Place products order | User |  | Average |  |  | User has to enter all the details of product order and so that order is placed successfully is shown
12 | 12 | document | M | US:12 | Display raw material order details | User |  | Complex |  |  | User has to enter delivery status, suppiler Id and get all the details of all the raw materials orders placed.
13 | 13 | document | M | US:13 | Display product order details | User |  | Complex |  |  | User has to enter delivery status, distributor Id and get all the details of all the product orders placed
14 | 14 | document | M | US:14 | Display Supplier details | User |  | Average |  |  | User has to enter supplier id and get all the details of the specified suppliers
15 | 15 | document | M | US:15 | Display distributor details | User |  | Average |  |  | User has to enter distributor id and get all the details of the specified distributors
Sprint 1 | Sprint 1
16 | 16
17 | 17
18 | 18
19 | 19
20 | 20
21 | 21
22 | 22
23 | 23
24 | 24
25 | 25
26 | 26
27 | 27
28 | 28
29 | 29
30 | 30
31 | 31
32 | 32
33 | 33
34 | 34
35 | 35
36 | 36
37 | 37
38 | 38
39 | 39
40 | 40
41 | 41
42 | 42
43 | 43
44 | 44
45 | 45
46 | 46
47 | 47
When using a Scrum approach to project management, use this sheet to document the Product Backlog, as captured in User Stories.

## Sprint Backlog (Scrum)
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
| US.nnn | 1
2
3
| US.nnn | 1
2
3
4
5
List User Story steps that were not completed at Sprint End
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.